## Sheet1
Bảng tổng hợp kiểm thử thủ công
Tên dự án | XÂY DỰNG HỆ THỐNG QUẢN LÝ PHÒNG TRỌ |  |  | Creator |  | Nhóm 5
Project Code | Nhom5_KiemThuPhanMem_49K14.2 |  |  | Reviewer/Approver
|  |  |  | Issue Date |  | 2026-04-29
|  |  | Vòng 1 |  |  |  | Vòng 2
STT | Module code | Tổng TH | Hoàn thành | Lỗi | Chưa hoàn thành | Ngày kiểm tra | Hoàn thành | Lỗi | Chưa hoàn thành | Ngày kiểm tra
1 | Trang Đăng nhập | 10 | 10 | 0 | 0 | 2026-04-22 | 10 | 0 | 0 | 2026-04-24
2 | Trang phòng | 10 | 10 | 0 | 0 | 2026-04-22 | 10 | 0 | 0 | 2026-04-24
3 | Quản lý phòng | 63 | 63 | 0 | 0 | 2026-04-20 | 63 | 0 | 0 | 2026-04-24
4 | Trang Khách thuê | 9 | 9 | 0 | 0 | 2026-04-22 | 9 | 0 | 0 | 2026-04-24
5 | Quản lý Khách thuê | 63 | 61 | 2 | 0 | 2026-04-20 | 61 | 2 | 0 | 2026-04-24
6 | Trang hợp đồng | 8 | 8 | 0 | 0 | 2026-04-22 | 8 | 0 | 0 | 2026-04-24
7 | Quản lý hợp đồng | 34 | 32 | 2 | 0 | 2026-04-22 | 32 | 2 | 0 | 2026-04-24
| Sub total | 197 | 193 | 4 | 0 |  | 193 | 4 | 0
|  |  |  | Vòng 1 | Vòng 2
| Kiểm tra vùng phủ sóng thành công |  |  | 97.97% | 97.97%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ?